## Backlog
Feature | User story | MoSCoW | Details | Status | Assignee
All | Define model objects for users and sessions | Must Have | User: - proposed fields: gender, first name, last name, email, phone number, password Session: - proposed fields: start date/time, end date/time | To do
Login | Add login operation | Must Have | Create controller, Mappings for endpoints, … | To do
Login | Add html form for login page | Must Have | Fields: username (email), password | To do
Login | Store session information | Must Have | Create mechanism for session management (store/retrieve session details) | To do
Login | Add html page for displaying the list of sessions of a logged in user | Must Have | Details to be included in the page: sessions table, each session to have start date/end date | To do
Login | Validations and error handling for login form | Should Have | Validations for field values: not empty / allowed characters / etc. | To do
Login | Forgot password | Could Have | Password reset using email link | To do
Login | Forgot username (email) | Could Have | Email recovery using phone number | To do
Login | Remember me option | Could Have |  | To do
Login | Automatic session expiry | Could Have |  | To do
Login | Login with other providers (google, facebook, etc.) | Could Have |  | To do
Login | Login with device fingerprint | Could Have |  | To do
Registration | Add register user operation | Must Have | Create controller, Mappings for endpoints, … | To do
Registration | Add html form for registration page | Must Have | Create mechanism for user management (store/retrieve details) | To do
Registration | Store user information | Must Have | Create mechanism for user management (store/retrieve details) | To do
Registration | Add validations for the registration form | Should Have | Values entered to follow some patterns | To do
Registration | Add verification flow | Could Have | Email validation / phone number validation | To do